## Readiness Tracker
Transition Readiness Tracker: one row for each thing that has to be true before go-live | [9 empty] | Status as of |  | Uses today's date. Type a fixed date to freeze it.
Claimed done is not proven. Mark an item Proven only after your team has seen the evidence in column C. Days late and Flag fill in automatically.
Area | Readiness item (what has to be true) | How we'll know (evidence) | Our owner | Provider owner | Needed by | Status | Critical for go-live? | Waiting on our side? | Go-live impact if late (days) | Days late (auto) | Flag (auto) | Notes and next action
People | Provider transition manager named and dedicated (not the account executive) | Named person working full time on the transition, with a written role |  |  |  |  | Yes
People | Our transition manager named, with time and decision authority | Named person, other work reassigned, and the executive sponsor has confirmed their authority |  |  |  |  | Yes | Yes
People | Affected internal team told what is changing and what happens to them | Communication delivered with HR, and open questions are being answered |  |  |  |  | No | Yes
People | Key knowledge holders have time set aside for knowledge transfer | Sessions are on calendars and their normal workload is covered |  |  |  |  | Yes | Yes
People | Provider team hired, cleared and onboarded | Named roster, with background checks and required onboarding complete |  |  |  |  | Yes
People | Provider team can do the work (reverse shadowing passed) | Our people watched them handle real work, including exceptions, and signed off |  |  |  |  | Yes
Process | Level 3 process map approved for each process in scope | Maps show inputs, systems, decisions, exceptions and handoffs, and our process owner approved them |  |  |  |  | Yes
Process | Procedures written so someone new could follow them | Our process owner reviewed and approved the procedures the provider will use |  |  |  |  | Yes
Process | Exceptions and escalation rules documented | The weird cases are written down, with who decides |  |  |  |  | Yes
Process | Handoffs with our other teams agreed | Who sends what, when and in what format, agreed by both sides |  |  |  |  | Yes
Process | SLA reporting works on real data | A sample SLA report produced from real transactions before go-live |  |  |  |  | Yes
Technology | Technical access log complete, with a named owner on our side for every item | Every credential, license, device and approval listed with an owner and a date |  |  |  |  | Yes | Yes
Technology | Access tested by the provider's actual operators | Each operator logged in with their own account and completed a real transaction |  |  |  |  | Yes
Technology | Equipment delivered and working | Hardware and software in place and tested by the people who will use it |  |  |  |  | No
Technology | Security review and approvals complete | Security sign-off documented for the provider's access and locations |  |  |  |  | Yes | Yes
Technology | Data and systems ready for go-live | Migration or test environment rehearsal completed and results reviewed |  |  |  |  | Yes | Yes
Governance | War room and meeting schedule set through hypercare | Recurring sessions on calendars with named attendees |  |  |  |  | No
Governance | Escalation path with named decision makers on both sides | Written path with names and response times |  |  |  |  | Yes
Governance | Weekly review of what our side owes the transition | Our open items in this tracker reviewed every week, with dates and go-live impact |  |  |  |  | No | Yes
Governance | Go/no-go criteria agreed, with who decides | Written criteria and decision makers, agreed before the date gets close |  |  |  |  | Yes | Yes
Governance | Fallback plan written, with people still available to run it | Named fallback steps and owners who have not been reassigned |  |  |  |  | Yes
Governance | Parallel run completed, if the work needs one | Both teams ran the same work and the results were compared |  |  |  |  | No
Governance | Hypercare exit criteria agreed | Written criteria for ending the extra support after go-live |  |  |  |  | No

## Go-Live Summary
Go-Live Summary
Column B reads your Readiness Tracker and column C the fictional example (rows 4 to 63 of each). Numbers update as you edit. This summary never approves go-live.
| Your tracker | Fictional example
Status as of
Items entered
Proven
Accepted risk
Not needed
Claimed done, not yet proven
Not started, in progress or no status
Critical items not proven (accepted risks and not needed are excluded)
...of which only claimed done
Late items
Late items waiting on our side
Largest delay estimate for a late item on our side (days)
Reading
Critical items accepted as a risk (check who accepted each one)
By area: your tracker | Items | Proven | Critical not proven | Late | Late on our side
People
Process
Technology
Governance
By area: fictional example | Items | Proven | Critical not proven | Late | Late on our side
People
Process
Technology
Governance
How to use this workbook
1. Open the fictional example first to see how a filled tracker reads two weeks before go-live.
2. On the Readiness Tracker, edit the starter items and add your own. Give every item a named person in the Our owner column.
3. Use Proven only when your team has seen the evidence. Training complete, request submitted and looks good are claims, not proof.
4. When something waiting on our side is late, ask the provider's transition manager for the go-live impact in days and enter it.
5. Review this summary before every weekly transition meeting. What's proven? What's only claimed? What are we blocking?
Stakeholders | Your map | Fictional example
Stakeholder groups listed
Groups with nobody named
Sign-offs with nobody named
Reading

## Stakeholder Map
Stakeholder Map: everyone who owns, approves or needs to hear about the transition
Put a person's name next to every group, or write Not applicable. Red means a sign-off has nobody named. Internal only = Yes rows never go to the provider.
Stakeholder group | Name(s) | Side | What they own, approve or decide | Sign-off they give | What they need from us | How often | Channel | Internal only? | Last update sent | Notes and gaps
Executive sponsor |  | Ours | The go/no-go call, accepting remaining risks, changes to go-live or hypercare dates | Go/no-go decision; hypercare exit | Five lines a week: confidence, top risks, decisions needed, what our side is blocking | Weekly | Email and steering committee | No
Our transition manager |  | Ours | Runs our side day to day and keeps this workbook current | Weekly readiness review | Everything on the tracker that is late, claimed or at risk | Daily | Working sessions | No
Steering committee |  | Both | Escalations and decisions that cross teams |  | One-page update with decisions needed | Every two weeks | Meeting | No
Provider transition manager |  | Provider | The provider's transition plan, dates and the go-live impact of anything late |  | What we owe them and by when | Weekly | Weekly transition review | No
Provider delivery lead |  | Provider | Running the service after go-live | Hypercare readiness | Exception rules, handoffs and what good looks like | Weekly | Weekly transition review | No
Process owners |  | Ours | Approving process maps, procedures and exception rules | Procedures approved; reverse shadowing passed | Drafts to review, with dates | Weekly | Working sessions | No
People who know the work (subject matter experts) |  | Ours | Teaching the work and watching the provider do it | Reverse shadowing observed | Time set aside, and what happens to them (from HR) | Weekly | Team meeting | Yes
Team whose work is moving |  | Ours | Their own day-to-day work during the transition |  | What is changing, when, and what it means for them (from HR) | As agreed with HR | Team meeting and 1:1s | Yes
HR and employee relations |  | Ours | Timing of people communications, retention plans and legal requirements for affected employees | People communications | Any change to dates or scope that affects people | Weekly | 1:1 | Yes
Works council or union (where one applies) |  | Other | Consultation rights before changes to jobs | Consultation complete | Whatever the law or agreement requires, through HR and legal | As required | Formal, through HR | Yes
IT identity and access |  | Ours | Accounts, VPN, licenses and devices for the provider's people | Access tested by the provider's operators | The access log, names and dates | Weekly | Access stand-up | No
Information security |  | Ours | Security review of the provider's access and locations | Security sign-off | Which systems, data and locations are in scope | At each review point | Email | No
Privacy and data protection |  | Ours | Approving provider access to personal or sensitive data | Data protection review | What data the provider will see, and from where | At each review point | Email | No
Legal and contracts |  | Ours | Contract schedules, change requests and formal notices | Contract changes | Proposed changes to dates, scope or obligations | As needed | Email | Yes
Finance and budget owner |  | Ours | Transition costs, the savings baseline and the provider's invoices | Budget changes | The cost of delays and extra hypercare | Monthly | Email | Yes
Procurement or vendor management |  | Ours | The commercial relationship and contract governance after go-live | Commercial changes | Anything the provider asks to change | Every two weeks | Email | No
Internal audit, risk and controls |  | Ours | Controls that change with the new process (for example SOX controls) | Controls documented for the new process | Changes to key controls and who performs them | At each review point | Email | No
Teams that hand work in or out |  | Ours | Handoffs into and out of the work that is moving | Handoff agreements | What changes for them, when, and in what format | Every two weeks | Email | No
Business users, customers and suppliers who will notice |  | Other | Requests, inquiries and the service they receive |  | What changes, when, and who to ask | Before and at go-live | Announcement or letter | No
Training and communications |  | Ours | Materials and announcements for people outside the core team |  | Dates, changes and FAQs | Every two weeks | Email | No
Facilities and badging |  | Ours | On-site access, desks and badges |  | Who needs access, where and when | As needed | Ticket or email | No
Outgoing provider (if you are replacing one) |  | Other | Exit assistance, data and knowledge handover | Handover complete | Dates and data requests, per their contract | Weekly | Formal, per their contract | Yes

## Run it with AI
Run this tracker with the AI you already have
Copy-ready prompts, setup steps for Microsoft 365 Copilot, ChatGPT and Gemini, and the rules for using AI on transition data are on this page:
https://www.yourscalex.com/outsourcing-transition-ai-kit.html
When | Routine | Prompt on the web page | What you get | Minutes
Once, at kickoff | Teach your AI the transition and the rules | 1. Project instructions | Your assistant knows the tracker's columns, statuses and rules | 10
Once, at kickoff | Build the tracker from the contract, plan and email | 2. Build the tracker | Missing rows, our dependencies with no owner, and open questions | 20
At kickoff, then monthly | Find every stakeholder | 3. Find every stakeholder | A filled Stakeholder Map and the groups nobody owns | 15
Every Monday | The weekly sweep | 4. The Monday sweep | Row updates with sources, claims without proof, our late items and draft nudges | 20
Before each weekly review | Done, or proven? | 5. Done, or proven? | The exact evidence to ask for on every critical claim | 10
When the provider's status report arrives | Watermelon check | 6. Watermelon check | Green items with no proof, date mismatches and questions to ask | 10
After each review or steering meeting | Turn the meeting into decisions | 7. Meeting to decisions | Decisions, who made them, actions, accepted risks and a recap email | 10
Two weeks and three days before go-live | Go/no-go pre-read | 8. Go/no-go pre-read | Each criterion met or not, with evidence, and who still has to sign off | 20
Weekly during hypercare | Hypercare exit check | 9. Hypercare exit check | Exit criteria met or not, and a draft extend-or-exit note | 15
Every Friday | Stakeholder updates | 10. Stakeholder updates | Sponsor, steering committee, provider-safe and business-user versions | 15
The rules
1. The AI suggests. Named people decide, especially go/no-go, risk acceptance and anything about people's jobs.
2. Nothing becomes Proven because someone said it's done. Proven means our team has seen the evidence.
3. Every suggested change names its source: an email, a meeting or a file.
4. Internal-only rows and anything about individual employees never go into a message or file for the provider.
5. Only use AI tools and connections your company has approved for this data. No approved tool? Practice on the fictional example.

## Example (fictional)
FICTIONAL EXAMPLE: Harborlight Mutual is moving accounts payable invoice processing to Quillmark Operations | [9 empty] | Status as of | 2026-10-05 | Fixed date for this example.
Both companies and every name are invented. Go-live is planned for October 19, 2026. Read the Flag column, then open Go-Live Summary for the reading.
Area | Readiness item (what has to be true) | How we'll know (evidence) | Our owner | Provider owner | Needed by | Status | Critical for go-live? | Waiting on our side? | Go-live impact if late (days) | Days late (auto) | Flag (auto) | Notes and next action
People | Provider transition manager named and dedicated (not the account executive) | Named person working full time on the transition, with a written role | D. Morales | S. Iyer | 2026-08-17 | Proven | Yes | No |  |  |  | Full time on the transition since kickoff.
People | Our transition manager named, with time and decision authority | Named person, other work reassigned, and the executive sponsor has confirmed their authority | K. Walsh | S. Iyer | 2026-08-17 | Proven | Yes | Yes |  |  |  | D. Morales named as our transition manager and released from month-end close work through November.
People | Affected internal team told what is changing and what happens to them | Communication delivered with HR, and open questions are being answered | L. Park |  | 2026-08-24 | Proven | No | Yes |  |  |  | Two Q&A sessions held. Retention agreements in place for two senior clerks.
People | Key knowledge holders have time set aside for knowledge transfer | Sessions are on calendars and their normal workload is covered | T. Nguyen | R. Costa | 2026-09-07 | Proven | Yes | Yes |  |  |  | Temporary backfill covers the senior clerks during sessions.
People | Provider team hired, cleared and onboarded | Named roster, with background checks and required onboarding complete | D. Morales | R. Costa | 2026-09-14 | Proven | Yes | No |  |  |  | 12 of 12 roles filled and cleared.
People | Provider team can do the work (reverse shadowing passed) | Our people watched them handle real work, including exceptions, and signed off | T. Nguyen | R. Costa | 2026-10-09 | Claimed done | Yes | No |  |  |  | Provider reports training complete. Our team has not yet watched them handle duplicate or disputed invoices.
Process | Level 3 process map approved for each process in scope | Maps show inputs, systems, decisions, exceptions and handoffs, and our process owner approved them | T. Nguyen | S. Iyer | 2026-09-11 | Proven | Yes | No |  |  |  | Approved for invoice intake, matching and exceptions.
Process | Procedures written so someone new could follow them | Our process owner reviewed and approved the procedures the provider will use | T. Nguyen | R. Costa | 2026-09-25 | Proven | Yes | No |  |  |  | Approved after two rounds of edits.
Process | Exceptions and escalation rules documented | The weird cases are written down, with who decides | T. Nguyen | R. Costa | 2026-10-09 | In progress | Yes | No |  |  |  | Disputed invoice rules are still being written.
Process | Handoffs with our other teams agreed | Who sends what, when and in what format, agreed by both sides | D. Morales | S. Iyer | 2026-09-25 | Proven | Yes | No |  |  |  | Agreed with procurement and treasury.
Process | SLA reporting works on real data | A sample SLA report produced from real transactions before go-live | T. Nguyen | S. Iyer | 2026-10-12 | In progress | Yes | No |  |  |  | First sample report due October 8.
Technology | Technical access log complete, with a named owner on our side for every item | Every credential, license, device and approval listed with an owner and a date | J. Ortiz | P. Novak | 2026-08-31 | Proven | Yes | Yes |  |  |  | 37 items, each with a named owner.
Technology | Access tested by the provider's actual operators | Each operator logged in with their own account and completed a real transaction | J. Ortiz | P. Novak | 2026-09-28 | Proven | Yes | No |  |  |  | All 12 operators completed a test invoice with their own accounts.
Technology | Equipment delivered and working | Hardware and software in place and tested by the people who will use it | J. Ortiz | P. Novak | 2026-09-28 | Claimed done | No | No |  |  |  | Provider says the scanners are installed. Nobody has tested them yet.
Technology | Security review and approvals complete | Security sign-off documented for the provider's access and locations | M. Adeyemi | P. Novak | 2026-09-21 | Proven | Yes | Yes |  |  |  | Signed off September 18.
Technology | Data and systems ready for go-live | Migration or test environment rehearsal completed and results reviewed | J. Ortiz | P. Novak | 2026-10-01 | In progress | Yes | Yes | 11 |  |  | Vendor master extract from our ERP team is 4 days late. Provider transition manager says go-live moves 11 days because the migration rehearsal and trainers must be rebooked.
Governance | War room and meeting schedule set through hypercare | Recurring sessions on calendars with named attendees | D. Morales | S. Iyer | 2026-10-12 | Proven | No | No |  |  |  | Daily at 8:30 during go-live week, then twice a week.
Governance | Escalation path with named decision makers on both sides | Written path with names and response times | K. Walsh | S. Iyer | 2026-09-25 | Proven | Yes | No |  |  |  | Named on both sides, with a 24-hour response for critical issues.
Governance | Weekly review of what our side owes the transition | Our open items in this tracker reviewed every week, with dates and go-live impact | D. Morales |  | 2026-09-08 | Proven | No | Yes |  |  |  | Reviewed every Tuesday since September 8.
Governance | Go/no-go criteria agreed, with who decides | Written criteria and decision makers, agreed before the date gets close | K. Walsh | S. Iyer | 2026-09-28 | Proven | Yes | Yes |  |  |  | Written and signed by both sponsors.
Governance | Fallback plan written, with people still available to run it | Named fallback steps and owners who have not been reassigned | D. Morales |  | 2026-10-12 | Accepted risk | Yes | No |  |  |  | Fallback relies on two retained clerks through November 30. K. Walsh accepted the risk that one may leave early.
Governance | Parallel run completed, if the work needs one | Both teams ran the same work and the results were compared | T. Nguyen | S. Iyer |  | Not needed | No | No |  |  |  | Staged handover by invoice type instead of a full parallel run.
Governance | Hypercare exit criteria agreed | Written criteria for ending the extra support after go-live | D. Morales | S. Iyer | 2026-10-16 | Not started | No | No |  |  |  | Draft criteria due at the October 13 review.

## Stakeholders (fictional)
FICTIONAL EXAMPLE: Harborlight Mutual's Stakeholder Map as of October 5, 2026
Same invented transition as Example (fictional). Three groups still have nobody named, and two of them give a sign-off the contract requires before go-live.
Stakeholder group | Name(s) | Side | What they own, approve or decide | Sign-off they give | What they need from us | How often | Channel | Internal only? | Last update sent | Notes and gaps
Executive sponsor | K. Walsh | Ours | The go/no-go call, accepting remaining risks, changes to go-live or hypercare dates | Go/no-go decision; hypercare exit | Five lines a week: confidence, top risks, decisions needed, what our side is blocking | Weekly | Email and steering committee | No | 2026-10-02 | Will decide on October 8 whether go-live moves if the ERP extract is late.
Our transition manager | D. Morales | Ours | Runs our side day to day and keeps this workbook current | Weekly readiness review | Everything on the tracker that is late, claimed or at risk | Daily | Working sessions | No | 2026-10-05 | Also owns the draft hypercare exit criteria, due October 13.
Steering committee | K. Walsh (chair), D. Morales, T. Nguyen, G. Silva, S. Iyer, R. Costa | Both | Escalations and decisions that cross teams |  | One-page update with decisions needed | Every two weeks | Meeting | No | 2026-10-02 | Next meeting October 16.
Provider transition manager | S. Iyer | Provider | The provider's transition plan, dates and the go-live impact of anything late |  | What we owe them and by when | Weekly | Weekly transition review | No | 2026-10-05 | M. Grant is Quillmark's account executive, not the transition manager.
Provider delivery lead | R. Costa | Provider | Running the service after go-live | Hypercare readiness | Exception rules, handoffs and what good looks like | Weekly | Weekly transition review | No | 2026-10-05 | Reverse shadowing planned for October 7 and 8.
Process owners | T. Nguyen | Ours | Approving process maps, procedures and exception rules | Procedures approved; reverse shadowing passed | Drafts to review, with dates | Weekly | Working sessions | No | 2026-10-05 | Waiting on a Treasury decision about duplicate invoices over $25k.
People who know the work (subject matter experts) | B. Hale, C. Duarte | Ours | Teaching the work and watching the provider do it | Reverse shadowing observed | Time set aside, and what happens to them (from HR) | Weekly | Team meeting | Yes | 2026-09-28 | Internal only: see HR notes. Fallback plan depends on both.
Team whose work is moving | AP clerks, through L. Park | Ours | Their own day-to-day work during the transition |  | What is changing, when, and what it means for them (from HR) | As agreed with HR | Team meeting and 1:1s | Yes | 2026-08-24 | Two Q&A sessions held in August.
HR and employee relations | L. Park | Ours | Timing of people communications, retention plans and legal requirements for affected employees | People communications | Any change to dates or scope that affects people | Weekly | 1:1 | Yes | 2026-10-02 | Internal only. Retention and resignation details stay with HR and the sponsor.
Works council or union (where one applies) | Not applicable | Other | Consultation rights before changes to jobs | Consultation complete | Whatever the law or agreement requires, through HR and legal | As required | Formal, through HR | Yes |  | No works council for this US team. Confirmed with L. Park.
IT identity and access | J. Ortiz | Ours | Accounts, VPN, licenses and devices for the provider's people | Access tested by the provider's operators | The access log, names and dates | Weekly | Access stand-up | No | 2026-10-01 | Also chasing the ERP extract with R. Bhatt.
Information security | M. Adeyemi | Ours | Security review of the provider's access and locations | Security sign-off | Which systems, data and locations are in scope | At each review point | Email | No | 2026-09-18 | Security sign-off covered operator access only, not supplier bank details.
Privacy and data protection |  | Ours | Approving provider access to personal or sensitive data | Data protection review | What data the provider will see, and from where | At each review point | Email | No |  | Nobody named. Supplier bank details need a data protection review before the rehearsal, and nobody has asked for it.
Legal and contracts | Contracts counsel, through G. Silva | Ours | Contract schedules, change requests and formal notices | Contract changes | Proposed changes to dates, scope or obligations | As needed | Email | Yes | 2026-09-21
Finance and budget owner | K. Walsh | Ours | Transition costs, the savings baseline and the provider's invoices | Budget changes | The cost of delays and extra hypercare | Monthly | Email | Yes | 2026-09-30 | An 11-day delay means paying for the current team and Quillmark at the same time.
Procurement or vendor management | G. Silva | Ours | The commercial relationship and contract governance after go-live | Commercial changes | Anything the provider asks to change | Every two weeks | Email | No | 2026-10-03 | Quillmark wants its own SLA dashboard instead of our template.
Internal audit, risk and controls |  | Ours | Controls that change with the new process (for example SOX controls) | Controls documented for the new process | Changes to key controls and who performs them | At each review point | Email | No |  | Nobody named. The contract says Internal Audit confirms key AP controls before go-live.
Teams that hand work in or out | R. Bhatt (ERP), A. Kim (Treasury), mailroom lead | Ours | Handoffs into and out of the work that is moving | Handoff agreements | What changes for them, when, and in what format | Every two weeks | Email | No | 2026-09-30 | R. Bhatt's vendor master extract is late and blocks the migration rehearsal.
Business users, customers and suppliers who will notice |  | Other | Requests, inquiries and the service they receive |  | What changes, when, and who to ask | Before and at go-live | Announcement or letter | No |  | Nobody named. Suppliers must be told the new invoice address by October 12.
Training and communications | D. Morales | Ours | Materials and announcements for people outside the core team |  | Dates, changes and FAQs | Every two weeks | Email | No | 2026-09-14
Facilities and badging | Not applicable | Ours | On-site access, desks and badges |  | Who needs access, where and when | As needed | Ticket or email | No |  | Work is done at Quillmark's delivery center. No on-site access needed.
Outgoing provider (if you are replacing one) | Not applicable | Other | Exit assistance, data and knowledge handover | Handover complete | Dates and data requests, per their contract | Weekly | Formal, per their contract | Yes |  | Work is moving from our own team, not from another provider.